## Project Planner
Tank Mania Plan
| . |  |  |  |  | Highlighted Period: | 1 |  |  | Plan Duration | [5 empty] | Task Start |  |  |  |  | % done |  |  |  |  | Behind the Plan | [7 empty] | % done (Behind the Plan)
ASSIGNEE | ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | % DONE | PERIODS
[7 empty] | 2022-04-25 | [13 empty] | 2022-05-10 | [20 empty] | 2022-05-24 | [13 empty] | 2022-06-14 | [13 empty] | 2022-06-28 | [13 empty] | 2022-07-12
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78
Common | 1. Milestone: Game idea Lecture: Softskills,Prototyping 1. Milestone: Game idea Lecture: Softskills,Prototyping Lecture: Softskills,Prototyping 1. Milestone: Game idea Lecture: Softskills,Prototyping eeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeeee | 1 | 14 | 1 | 14 | 0% | 2022-04-25 1: Project Proposal Document
Common | 2. Milestone: Prototype | 15 | 21 | 15 | 21 | 0% | 2022-05-10 15: Paper Prototype
Common | 3. Milestone: Interim demo | 36 | 14 | 36 | 14 | 0% | 2022-05-24 36: Finish Layer 2 Work well into layer 3
Common | 4. Milestone: Alpha release Lecture: Playtesting | 50 | 14 | 50 | 14 | 0% | 2022-06-14 50: Alpha release, demo game and playtesting with friends
Common | 5. Milestone: Playtesting | 64 | 14 | 64 | 14 | 0% | 2022-06-28 64: Proper playtesting and outcome presentation
Common | 6. Milestone: Final release | 78 | 1 | 78 | 1 | 0%
Common | General Game Idea | 1 | 8 | 1 | 7 | 0%
Janosch | Game Description Composition | 5 | 6 | 3 | 5 | 0%
Janosch | Technical Achievement Description | 7 | 6 | 7 | 5 | 0%
Doğa | "Big Idea" Bullseye Structure | 6 | 7 | 9 | 4 | 0%
Mykola | Development Schedule Formulation | 5 | 7 | 5 | 8 | 0%
Doğa | Results Assessment | 9 | 5 | 11 | 3 | 0%
Common | Game Mechanics Paper Transition | 15 | 12 | 0 | 0 | 0%
Common | Physical Game Asset Creation | 19 | 14 | 0 | 0 | 0%
Common | Prototype Playtesting | 21 | 11 | 0 | 0 | 0%
Common | Prototype Presentation Training | 24 | 11 | 0 | 0 | 0%
Doğa | Playable Tank Shooting | 26 | 10 | 0 | 0 | 0%
Doğa | Playable Tank Movement | 28 | 3 | 0 | 0 | 0%
Mykola | Procedural Level Generation Basis | 27 | 11 | 0 | 0 | 0%
Mykola | Roaming AI Creation | 29 | 14 | 0 | 0 | 0%
Janosch | Multiplayer Setup | 31 | 13 | 0 | 0 | 0%
Doğa | Power-up System | 33 | 4 | 0 | 0 | 0%
Janosch | Performance Modifier and Skillshot System | 36 | 6 | 0 | 0 | 0%
Mykola | AI Improvement | 50 | 12 | 0 | 0 | 0%
Mykola | Level Generation Parametrization | 55 | 8 | 0 | 0 | 0%
Janosch | Multiplayer Fail-Proofing | 53 | 10 | 0 | 0 | 0%
Doğa | UI/SFX Mocking | 52 | 9 | 0 | 0 | 0%
Common | White-box Playtesting | 64 | 5 | 0 | 0 | 0%
Janosch | General Bugfixing Round | 68 | 6 | 0 | 0 | 0%
Common | External Playtesting | 66 | 5 | 0 | 0 | 0%
Mykola | Feedback Collection | 70 | 5 | 0 | 0 | 0%
Doğa | Playtesting Report Gathering | 73 | 3 | 0 | 0 | 0%
Doğa | UI/Audio/SFX Finalization | 65 | 5 | 0 | 0 | 0%
Mykola | Asset Quality Improvement | 67 | 4 | 0 | 0 | 0%
Janosch | Code Optimization | 62 | 10 | 0 | 0 | 0%
Common | Production Build Preparation | 72 | 4 | 0 | 0 | 0%